## DTT Test Hour Log
Instruction: Fill in the number of hours that were required to complete the test. Please include every step you took during the process and include a detailed description of every step. Add reasoning on why you took certain decisions or applied specific techniques. We prefer quality over quantity so take your time with the test and the log.
Subject | Amount of hours | Date | Description | Bonus
Project setup | 1 | 15/08/2024 | Setting up the directories and Initial components.
Creating Vuex Store | 1 | 15/08/2024 | Setting up the vuex store with initial state for managing listings.
SCSS | 1 | 15/08/2024 | Implementing styling rules.
NavBar.vue component | 1 | 15/08/2024 | Creating the navigation bar component and styling it.
HousesPage | 3 | 15/08/2024 | Creating the main page of the website.
I used a container to keep everything in a given space for future ease.
Created a component for one House (HouseCard)
Another component that is used for listing all the Houses.
Setting up axios for fetching data | 0.5 | 16/08/2024 | Setting up the vuex store to fetch data from API
Creating button component | 1 | 16/08/2024 | Creating a reusable button component
Working on single house component | 2 | 16/08/2024 | Fixed the styling issues I had with sass
Improved overall styles for the component
Refactoring the store | 1 | 16/08/2024 | Creating seperate store module for crud operations.
Switchbutton | 1 | 16/08/2024 | Created a component for sorting the listed houses
Search functionality | 1 | 16/08/2024 | Implenting filter for searching/refactoring in the store
Faced issues with replacing the clear icon.
No matches found page | .5 |  | Created page for no results found
Creating housedetail page | 1 | 16/08/2024 | Creating a seperate page for details of one house
Finished working on housedetail page | 1.5 | 17/08/2024 | Added additional styling to the page
Begin working on creationpage | 1 | 18/08/2024 | Started with the basic structure of the page
Finished styling of creationpage | 2 | 22/08/2024
Worked on posting the form | 2 | 22/08/2024 | Run into issues when trying to post a new house. Solved with first using regular fetch
and then refactoring with axios.
Worked on editing page | 3 | 24/08/2024 | I came across issues while using the vuex store for sending a new listing and editing. I was unable to solve it
Created backbutton | 1 | 24/08/2024 | Created a worling backbutton component
Deleting a listing | 1 | 26/08/2024 | Created popup component for deleting a lisiting.
Integrated deleting function in components | .5 | 26/08/2024 | Dealt with the intgration of the popup component
Refactored the codebase | 2 | 31/08/2024 | Rewrote the codebase
Created footer for phone case | 1 | 31/08/2024
Styling for phone | 2 | 31/08/2024
Final refactoring adding comments | 1 | 31/08/2024
Working About Page | 1 | 31/08/2024 |  | 1
Total amount of hours | 31